## Sheet1
Story Points | Ideal Tracking (Days) | Actual Tracking (Days) | Comments
0 | 15 | 15
1 | 13.929 | 15
2 | 12.858 | 12 | Blake/Alex: User Story 12 Completed
3 | 11.787 | 11 | Steph: Task 1 of User Story 8 Completed
4 | 10.716 | 11
5 | 9.645 | 9 | Blake/Ashleigh: User Story 11 Completed
6 | 8.574 | 9
7 | 7.503 | 9
8 | 6.432 | 8 | Blake: Task 2 of User Story 8 Completed
9 | 5.361 | 8
10 | 4.29 | 8
11 | 3.219 | 8
12 | 2.148 | 6 | Blake/Alex/Sophie/Steph: User Story 13 Completed
13 | 1.077 | 1 | Blake/Sophie: User Story 20 Completed. Dylan/Alex: Part of User Story 27 Completed
14 | 0 | 0 | Blake: User Story 27 Completed. Additional Tasks Completed